## Version
Version | Date | Author | Change
0.1 | 2024-02-14 | Cristian S | Initial Release
0.2 | 2024-02-21 | Cristian S | Added revew id to the review name and sheet in order to track and acknowledge solution from previous review phases.

## Usage
About
This is a hardware design review form to be used for reviewing hardware designs at 3E.
Usage
1. Copy the 'II_gitid' tab replace 'II' with your initials and 'gitid' with the gitid of the datapack you are just about to review.
a) create review notes in this newly created tab
b) make sure that the solution to previous reviews issues are adequate if not raise them again in this sheet but using the old issue id so that actions are trackable
2. Save this file under a new name by replacing the II in the file name with your initials.
a) check in this file onto the project review branch so that it can be actioned
b) if new issues are discovered before a new review is out just update this file in the repository
Legend
Reviewer input fields.
Author feedback fields.
Version | Modified | Changes
V06092024 | CS | Updated for the new automation process and to be used/triald on VMB board initial review.

## II_gitid
Issue ID | Issue Description | Proposed Solution | Implemented Solution | Issue Statu
20240214_01_RN Issue identified on the P1_NCC_V1 version 1 of the schematic. | Power dissipation in R4 and R5 (on page 2) is around 140mW (13.5^2/1300) this exceeds the power rating of the 125mW 0805 resistor in design. | User a 1206 footprint resistor this will have a power rating of 400mW. This solution will provide over 50% power margin and increased reliability. | In order to reduce the number of different components on the bom it's been decided to address the issue by placing two 0805 2.2k resistor in parallel. | 20240221_0900_RN I conirm that the solution has been inplemented in P1_NCC_V2 version 2 of the schematic and that this fully addresses issue 20240214_0226_RN.
20240214_02_RN Issue identified on the P1_NCC_V1 version 1 of the schematic.
Note on B1: Cristian: Provide a detailed description of the issue including location and how could the issue be reproduced if required.
Note on C1: Cristian: Provide a detailed proposed solution that would address and close the raised issue. Discuss the proposed soluion with the author such that the issue could be closed in one itteration.
Note on D1: Cristian: This field is to be filled in by the author/person responsible for the work that is currently being reviewd.
Note on E1: Cristian: This is to be filled in by the reviewer durring a subsequent review itteration. I should state if the issue was partially, fully or not addressed at all in which case a new isssue number should be open on the same issue for the current review.
Note on A2: Cristian: This is an example issue number containing the date, isue number (in) and reviewer name initials (ri) in the following format: yyyymmdd_in_ri